## Project Data
Sr. No. | Priority | Initiative ID | Initiative Details | Start Date (Planned) | End Date (Planned) | Start Date (Actual/ Estimate) | End Date (Actual/ Estimate) | Budget Type | Budget Status | Project Status | Traffic Light | Area of Concern | Category | Department | Budget Sub-Type | Estimated Benefit ($/T) | Project Level | Execution Status | Budget Sought (Rs. Cr.) | Budget Required FY23 | Budget Approved FY23 | Current Level Execution Status
1 | High | P001 | Project Detail 1 | 2020-08-10 | 2023-01-25 | 2020-08-10 | 2023-01-25 | Capital | Approved | Planned/ Ongoing/ Executed | Green | BTG Improvement | TPP | Boiler | Sustaining CAPEX Carryover | 3.9989 | L4 | On-track | 54 | 30 | 30 | Delayed from baseline & currently on-track
2 | Medium | P002 | Project Detail 2 | 2021-09-07 | 2022-05-14 | 2021-09-07 | 2022-07-28 | Capital | Approved | Planned/ Ongoing/ Executed | Red | BTG Improvement | TPP | Boiler | Sustaining CAPEX Carryover | 1.479 | L4 | Delayed | 6 | 6 | 6 | Delayed from baseline & currently on-track
3 | Medium | P003 | Project Detail 3 | 2021-09-07 | 2022-02-10 | 2021-09-07 | 2022-04-18 | Revenue | Approved | Planned/ Ongoing/ Executed | Green | BTG Improvement | TPP | Boiler | Revenue One-time | 0 | Complete | Complete | 3.3 | 0 | 0 | null
4 | High | P004 | Project Detail 4 | 2020-08-10 | 2022-09-07 | 2020-08-10 | 2022-09-07 | Capital | Approved | Planned/ Ongoing/ Executed | Green | BTG Improvement | TPP | Boiler | Sustaining CAPEX Carryover | 4.5133 | L4 | On-track | 54 | 7.5 | 7.5 | Delayed from baseline & running delayed
5 | High | P005 | Project Detail 5 | 2021-12-14 | 2024-05-25 | 2021-12-14 | 2024-05-25 | Capital | Approved | Planned/ Ongoing/ Executed | Green | BTG Improvement | TPP | Boiler | Project CAPEX | 39.469 | L2 | On-track | 538 | 163 | 163 | Delayed from baseline & currently on-track
6 | Medium | P006 | Project Detail 6 | 2021-07-01 | 2022-02-15 | 2021-07-01 | 2022-03-30 | Revenue | Approved | Planned/ Ongoing/ Executed | Green | BTG Improvement | TPP | Boiler | Revenue One-time | 0.19326 | Complete | Complete | 1.75 | 0 | 0 | null
7 | High | P007 | Project Detail 7 | 2022-01-01 | 2022-12-31 | 2022-01-01 | 2022-12-31 | Revenue | Approved | Planned/ Ongoing/ Executed | Green | BTG Improvement | TPP | Boiler | Revenue One-time | 0.23868 | L4 | On-track | 20 | 15 | 15 | Delayed from baseline & currently on-track
8 | Medium | P008 | Project Detail 8 | 2022-01-05 | 2022-02-25 | 2022-01-06 | 2022-02-25 | Not required | Not Applicable | Planned/ Ongoing/ Executed | Green | BTG Improvement | TPP | Boiler | Not required | 0.024158 | Complete | Complete | 0 | 0 | 0 | null
9 | Medium | P009 | Project Detail 9 | 2021-02-01 | 2022-02-22 | 2021-02-01 | 2022-02-22 | Revenue | Approved | Planned/ Ongoing/ Executed | Green | BTG Improvement | TPP | Boiler | Revenue Regular | 0.053704 | Complete | Complete | 0.2 | 0 | 0 | null
10 | High | P010 | Project Detail 10 | 2022-01-01 | 2022-09-15 | 2022-01-01 | 2022-09-15 | Revenue | Approved | Planned/ Ongoing/ Executed | Green | BTG Improvement | TPP | Boiler | Revenue Regular | 0 | L4 | On-track | 0.3 | 0 | 0 | Delayed from baseline & currently on-track
11 | Medium | P011 | Project Detail 11 | 2021-02-01 | 2022-02-22 | 2021-02-01 | 2022-09-20 | Revenue | Approved | Planned/ Ongoing/ Executed | Red | BTG Improvement | TPP | Boiler | Revenue One-time | 0.011815 | L4 | Delayed | 0.3 | 0 | 0 | Delayed from baseline & running delayed
12 | Medium | P012 | Project Detail 12 | 2022-01-05 | 2022-08-31 | 2022-01-06 | 2022-09-15 | Revenue | Approved | Planned/ Ongoing/ Executed | Red | BTG Improvement | TPP | Boiler | Revenue Regular | 0 | L4 | Delayed | 1 | 1 | 1 | Delayed from baseline & running delayed
13 | Medium | P013 | Project Detail 13 | 2022-01-01 | 2022-07-14 | 2022-01-01 | 2022-07-14 | Capital | Approved | Planned/ Ongoing/ Executed | Green | BTG Improvement | TPP | Boiler | Sustaining CAPEX New | 0.4912 | L2 | On-track | 3 | 0.9 | 0.9 | null
14 | Medium | P014 | Project Detail 14 | 2021-08-10 | 2022-03-31 | 2021-08-10 | 2022-07-04 | Not required | Not Applicable | Planned/ Ongoing/ Executed | Red | BTG Improvement | TPP | Boiler | Not required | 0 | L4 | Delayed | 0 | 0 | 0 | Delayed from baseline & currently on-track
15 | Medium | P015 | Project Detail 15 | null | null | null | null | Revenue | Approved |  | null | BTG Improvement | TPP | Boiler | Revenue One-time | 0 | Unavailable | Not yet started | 0.3 | 0.3 | 0.3 | null
16 | Medium | P016 | Project Detail 16 | 2022-02-01 | 2022-05-14 | 2022-02-01 | 2022-09-05 | Revenue | Unapproved | Planned/ Ongoing/ Executed | Red | BTG Improvement | TPP | Boiler | Revenue One-time | 0.41824 | L3 | Delayed | 2 | 2 | 0 | Delayed from baseline & running delayed
17 | Medium | P017 | Project Detail 17 | 2021-04-05 | 2022-03-15 | 2021-04-05 | 2022-06-30 | Revenue | Approved | Planned/ Ongoing/ Executed | Red | BTG Improvement | TPP | Turbine | Revenue One-time | 0.67 | L4 | Delayed | 0.6 | 0 | 0 | Delayed from baseline & currently on-track
18 | Medium | P018 | Project Detail 18 | 2021-10-01 | 2022-02-27 | 2021-10-01 | 2022-02-27 | Not required | Not Applicable | Planned/ Ongoing/ Executed | Green | BTG Improvement | TPP | Turbine | Not required | 0.080556 | Complete | Complete | 0 | 0 | 0 | null
19 | Medium | P019 | Project Detail 19 | 2022-02-01 | 2022-05-25 | 2022-01-31 | 2022-09-03 | Revenue | Approved | Planned/ Ongoing/ Executed | Red | BTG Improvement | TPP | Turbine | Revenue One-time | 0 | L4 | Delayed | 0.45 | 0.45 | 0.45 | Delayed from baseline & running delayed
20 | Medium | P022 | Project Detail 20 | 2021-12-03 | 2022-02-10 | 2021-01-03 | 2022-02-25 | Revenue | Approved | Planned/ Ongoing/ Executed | Green | BTG Improvement | TPP | Generator | Revenue One-time | 0 | Complete | Complete | 2 | 0 | 0 | null
21 | Medium | P023 | Project Detail 21 | 2021-08-23 | 2022-02-15 | 2021-08-23 | 2022-02-25 | Revenue | Approved | Planned/ Ongoing/ Executed | Green | BTG Improvement | TPP | Generator | Revenue One-time | 0 | Complete | Complete | 0 | 0 | 0 | null
22 | Medium | P024 | Project Detail 22 | 2022-02-01 | 2022-08-30 | 2022-02-01 | 2022-10-29 | Revenue | Unapproved | Planned/ Ongoing/ Executed | Red | BTG Improvement | TPP | Generator | Revenue One-time | 0 | L2 | Delayed | 0.5 | 0.5 | 0.5 | Delayed from baseline & running delayed
23 | Medium | P026 | Project Detail 23 | 2022-01-01 | 2022-12-31 | 2022-02-01 | 2023-03-31 | Revenue | Unapproved | Planned/ Ongoing/ Executed | Red | BTG Improvement | CPP | Boiler | Revenue One-time | 0 | L1 | Delayed | 3 | 3 | 0 | Delayed from baseline & currently on-track
24 | Medium | P027 | Project Detail 24 | 2021-10-01 | 2024-03-31 | 2021-10-01 | 2024-05-31 | Revenue | Approved | Planned/ Ongoing/ Executed | Red | BTG Improvement | CPP | Boiler | Revenue Regular | 0 | L3 | Delayed | 0 | 0 | 0 | Delayed from baseline & running delayed
25 | Medium | P028 | Project Detail 25 | 2021-12-01 | 2022-10-19 | 2021-12-01 | 2022-10-19 | Revenue | Approved | Planned/ Ongoing/ Executed | Green | BTG Improvement | CPP | Electrical | Revenue One-time | 0 | L4 | On-track | 3 | 3 | 3 | null
26 | Medium | P029 | Project Detail 26 | 2021-10-12 | 2022-03-13 | 2021-10-12 | 2022-05-19 | Revenue | Approved | Dropped | null | BTG Improvement | CPP | Boiler | Revenue Regular | 0 | Unavailable | Delayed | 2 | 2 | 2 | null
27 | Medium | P031 | Project Detail 27 | 2021-12-10 | 2022-05-10 | 2021-12-10 | 2022-06-01 | Revenue | Unapproved | Planned/ Ongoing/ Executed | Red | BTG Improvement | CPP | Turbine | Revenue One-time | 0 | L4 | Delayed | 0.45 | 0.45 | 0 | Delayed from baseline & running delayed
28 | Medium | P033 | Project Detail 28 | 2022-01-10 | 2022-11-30 | 2022-01-10 | 2022-11-30 | Revenue | Approved | Planned/ Ongoing/ Executed | Green | BTG Improvement | CPP | Turbine | Revenue One-time | 0.89552 | L4 | On-track | 1.8 | 1.8 | 1.8 | null
29 | Medium | P034 | Project Detail 29 | 2021-10-31 | 2022-07-31 | 2021-10-31 | 2022-07-31 | Revenue | Unapproved | Planned/ Ongoing/ Executed | Green | BTG Improvement | CPP | Turbine | Revenue One-time | 0.1194 | L3 | On-track | 0.3 | 0.3 | 0 | null
30 | Medium | P035 | Project Detail 30 | 2021-12-31 | 2022-07-30 | 2021-12-31 | 2022-07-30 | Not required | Not Applicable | Planned/ Ongoing/ Executed | Green | BTG Improvement | CPP | Turbine | Not required | 0 | L4 | On-track | 0 | 0 | 0 | null
31 | Medium | P036 | Project Detail 31 | 2021-12-01 | 2022-12-26 | 2021-12-01 | 2022-12-26 | Revenue | Approved | Planned/ Ongoing/ Executed | Green | BTG Improvement | CPP | Electrical | Revenue One-time | 0 | L4 | On-track | 5.5 | 5.5 | 5.5 | null
32 | Medium | P038 | Project Detail 32 | 2021-11-20 | 2022-10-14 | 2021-11-20 | 2022-12-23 | Revenue | Approved | Planned/ Ongoing/ Executed | Red | BTG Improvement | CPP | Electrical | Revenue One-time | 0 | L3 | Delayed | 6 | 6 | 6 | Delayed from baseline & running delayed
33 | Medium | P039 | Project Detail 33 | 2021-12-01 | 2022-11-03 | 2021-12-01 | 2022-11-03 | Revenue | Approved | Planned/ Ongoing/ Executed | Green | BTG Improvement | CPP | Electrical | Revenue One-time | 0 | L4 | On-track | 6 | 6 | 6 | null
34 | Medium | P040 | Project Detail 34 | 2021-12-01 | 2023-01-05 | 2021-12-01 | 2023-06-20 | Capital | Approved | Planned/ Ongoing/ Executed | Red | BTG Improvement | CPP | Electrical | Sustaining CAPEX Carryover | 0 | L3 | Delayed | 2.5 | 2.5 | 2.5 | Delayed from baseline & running delayed
35 | Medium | P041 | Project Detail 35 | 2021-09-08 | 2022-06-05 | 2021-09-08 | 2022-06-05 | Revenue | Approved | Planned/ Ongoing/ Executed | Green | BTG Improvement | CPP | Generator | Revenue One-time | 0 | L4 | On-track | 2 | 2 | 2 | null
36 | Medium | P042 | Project Detail 36 | 2022-01-25 | 2022-10-31 | 2022-01-25 | 2022-10-31 | Revenue | Approved | Planned/ Ongoing/ Executed | Green | BTG Improvement | CPP | Generator | Revenue One-time | 0 | L4 | On-track | 0.5 | 0.5 | 0.5 | null
37 | Medium | P043 | Project Detail 37 | 2021-10-31 | 2022-12-30 | 2021-09-30 | 2022-12-30 | Capital | Approved | Planned/ Ongoing/ Executed | Green | System Stability | BOP | Electrical | Sustaining CAPEX Carryover | 0 | L4 | On-track | 3.5 | 0.7 | 0.7 | null
38 | Medium | P044 | Project Detail 38 | 2021-10-31 | 2022-03-30 | 2021-10-31 | 2022-12-31 | Not required | Not Applicable | Planned/ Ongoing/ Executed | Red | System Stability | BOP | Electrical | Not required | 0 | L1 | Delayed | 0 | 0 | 0 | Delayed from baseline & running delayed
39 | Medium | P045 | Project Detail 39 | 2021-10-31 | 2022-03-30 | 2021-10-31 | 2022-12-31 | Capital | Approved | Planned/ Ongoing/ Executed | Red | System Stability | BOP | Electrical | Sustaining CAPEX New | 0 | L1 | Delayed | 12 | 12 | 3 | Delayed from baseline & running delayed
40 | High | P046 | Project Detail 40 | 2021-12-23 | 2023-03-06 | 2021-12-23 | 2023-03-06 | Capital | Approved | Planned/ Ongoing/ Executed | Green | System Stability | CPP | C&I | Sustaining CAPEX New | 0.9762 | L3 | On-track | 36.7 | 16 | 4.1 | Delayed from baseline & running delayed
41 | Medium | P047 | Project Detail 41 | 2019-01-10 | 2021-12-01 | 2019-01-10 | 2022-09-30 | Capital | Approved | Planned/ Ongoing/ Executed | Red | System Stability | CPP | Electrical | Sustaining CAPEX Carryover | 0.0090199 | L4 | Delayed | 11 | 0.3 | 0.3 | Delayed from baseline & currently on-track
42 | Medium | P048 | Project Detail 42 | 2021-08-10 | 2023-12-30 | 2021-08-10 | 2023-12-30 | Revenue | Approved | Planned/ Ongoing/ Executed | Green | System Stability | CPP | Electrical | Revenue One-time | 0 | L4 | On-track | 1.2 | 1.2 | 1.2 | null
43 | Medium | P049 | Project Detail 43 | 2020-01-10 | 2022-07-30 | 2020-01-10 | 2022-07-30 | Revenue | Approved | Planned/ Ongoing/ Executed | Green | System Stability | CPP | Electrical | Revenue One-time | 0 | L4 | On-track | 2 | 2 | 2 | null
44 | Medium | P050 | Project Detail 44 | 2019-01-10 | 2022-03-30 | 2019-01-10 | 2022-04-30 | Revenue | Approved | Planned/ Ongoing/ Executed | Green | System Stability | CPP | Electrical | Revenue Regular | 0 | Complete | Complete | 0.48 | 0.48 | 0.48 | null
45 | Medium | P051 | Project Detail 45 | 2022-03-01 | 2022-10-05 | 2022-03-01 | 2022-11-30 | Revenue | Unapproved | Planned/ Ongoing/ Executed | Red | System Stability | CPP | Electrical | Revenue One-time | 0 | L1 | Delayed | 0.2 | 0.2 | 0 | Delayed from baseline & currently on-track
46 | Medium | P052 | Project Detail 46 | 2022-03-20 | 2023-05-30 | 2022-01-25 | 2023-05-30 | Capital | Approved | Planned/ Ongoing/ Executed | Green | System Stability | TPP | Electrical | Sustaining CAPEX New | 0 | L2 | On-track | 5 | 3 | 1.3 | null
47 | Medium | P053 | Project Detail 47 | 2021-08-01 | 2022-05-30 | 2021-08-01 | 2022-07-31 | Capital | Approved | Planned/ Ongoing/ Executed | Red | System Stability | TPP | Electrical | Sustaining CAPEX Carryover | 0 | L4 | Delayed | 11 | 0.5 | 0.5 | Delayed from baseline & currently on-track
48 | Medium | P055 | Project Detail 48 | 2022-02-01 | 2023-02-28 | 2022-02-01 | 2023-02-28 | Revenue | Approved | Planned/ Ongoing/ Executed | Green | System Stability | CPP | Common | Revenue One-time | 0 | L3 | On-track | 2 | 2 | 2 | null
49 | Medium | P056 | Project Detail 49 | 2021-12-01 | 2023-01-06 | 2021-12-01 | 2023-01-06 | Revenue | Unapproved | Planned/ Ongoing/ Executed | Green | System Stability | CPP | Electrical | Revenue One-time | 0 | L4 | On-track | 1 | 1 | 0 | null
50 | Medium | P057 | Project Detail 50 | 2021-07-31 | 2022-09-30 | 2021-07-31 | 2022-09-30 | Revenue | Approved | Planned/ Ongoing/ Executed | Green | System Stability | BOP | Electrical | Revenue One-time | 0 | L4 | On-track | 0.2 | 0.2 | 0.2 | null
51 | Medium | P058 | Project Detail 51 | 2022-01-15 | 2023-01-04 | 2022-01-15 | 2023-02-03 | Capital | Approved | Planned/ Ongoing/ Executed | Red | System Stability | CPP | C&I | Sustaining CAPEX New | 0 | L2 | Delayed | 5 | 5 | 0.5 | Delayed from baseline & currently on-track
52 | Medium | P059 | Project Detail 52 | 2022-01-15 | 2024-03-31 | 2022-01-15 | 2024-04-30 | Capital | Approved | Planned/ Ongoing/ Executed | Red | System Stability | CPP | C&I | Sustaining CAPEX New | 0 | L2 | Delayed | 9 | 4 | 2.3 | Delayed from baseline & currently on-track
53 | Medium | P060 | Project Detail 53 | 2021-11-01 | 2022-09-30 | 2021-11-02 | 2022-09-30 | Revenue | Approved | Planned/ Ongoing/ Executed | Green | System Stability | CPP | C&I | Revenue One-time | 0 | L4 | Risk of Delay | 6 | 6 | 6 | null
54 | High | P061 | Project Detail 54 | 2021-04-10 | 2022-08-15 | 2021-04-10 | 2022-08-15 | Capital | Approved | Planned/ Ongoing/ Executed | Green | System Stability | Water | Electrical | Sustaining CAPEX Carryover | 0 | L4 | Risk of Delay | 6.5 | 0.5 | 0.5 | Delayed from baseline & currently on-track
55 | High | P062 | Project Detail 55 | 2021-06-05 | 2022-09-30 | 2021-06-05 | 2022-09-30 | Capital | Approved | Planned/ Ongoing/ Executed | Green | System Stability | Water | Electrical | Sustaining CAPEX Carryover | 0 | L4 | Risk of Delay | 6.3 | 6.2 | 6.2 | Delayed from baseline & currently on-track
56 | High | P063 | Project Detail 56 | 2022-05-10 | 2024-07-31 | 2022-05-10 | 2024-07-31 | Capital | Unapproved | Planned/ Ongoing/ Executed | Green | System Stability | Water | Water Security | Project CAPEX | 0 | L1 | Risk of Delay | 400 | 0 | 0 | Delayed from baseline & running delayed
57 | Medium | P064 | Project Detail 57 | 2021-12-25 | 2022-12-30 | 2021-12-25 | null | Capital | Not Applicable | Dropped | null | System Stability | Water | Water Security | Sustaining CAPEX New | 0 | Unavailable | Not yet started | 0 | 0 | 0 | null
58 | Medium | P065 | Project Detail 58 | 2022-01-01 | 2024-09-01 | 2022-01-01 | 2024-09-01 | Capital | Unapproved | Planned/ Ongoing/ Executed | Green | System Stability | Water | Electrical | Project CAPEX | 0 | L1 | On-track | 25 | 0 | 0 | null
59 | High | P066 | Project Detail 59 | 2021-03-01 | 2024-02-15 | 2021-03-01 | 2024-02-15 | Capital | Approved | Planned/ Ongoing/ Executed | Green | System Stability | Water | Water Security | Sustaining CAPEX New | 0.58089 | L2 | On-track | 250 | 45 | 45 | Delayed from baseline & running delayed
60 | High | P067 | Project Detail 60 | 2021-11-25 | 2022-08-23 | 2021-10-31 | 2022-08-23 | Capital | Approved | Planned/ Ongoing/ Executed | Green | System Stability | Water | Water Security | Sustaining CAPEX Carryover | 0 | L4 | On-track | 6.9 | 6.9 | 6.9 | Delayed from baseline & running delayed
61 | Medium | P068 | Project Detail 61 | 2021-06-02 | 2022-03-15 | 2021-06-02 | 2022-03-15 | Capital | Approved | Planned/ Ongoing/ Executed | Green | System Stability | TPP | Common | Sustaining CAPEX Carryover | 0 | Complete | Complete | 3.5 | 0 | 0 | null
62 | Medium | P069 | Project Detail 62 | 2021-05-14 | 2022-06-25 | 2021-05-14 | 2022-09-30 | Capital | Approved | Planned/ Ongoing/ Executed | Red | System Stability | TPP | Common | Sustaining CAPEX Carryover | 0.024587 | L4 | Delayed | 2.5 | 2.5 | 2.5 | Delayed from baseline & currently on-track
63 | Medium | P070 | Project Detail 63 | 2021-11-01 | 2023-06-30 | 2021-11-01 | 2023-09-15 | Capital | Approved | Planned/ Ongoing/ Executed | Red | System Stability | TPP | Common | Sustaining CAPEX New | 0.049173 | L2 | Delayed | 14 | 7 | 2 | Delayed from baseline & currently on-track
64 | High | P071 | Project Detail 64 | 2022-02-01 | 2023-03-25 | 2022-02-01 | 2023-03-25 | Revenue | Approved | Planned/ Ongoing/ Executed | Green | System Stability | CPP | Common | Revenue One-time | 0 | L3 | On-track | 0.2 | 0.2 | 0.2 | Delayed from baseline & running delayed
65 | Medium | P072 | Project Detail 65 | 2022-01-07 | 2022-09-30 | 2022-01-20 | 2022-12-29 | Revenue | Approved | Planned/ Ongoing/ Executed | Red | System Stability | TPP | Common | Revenue One-time | 0.062441 | L1 | Delayed | 2 | 2 | 2 | Delayed from baseline & running delayed
66 | Medium | P073 | Project Detail 66 | 2021-09-08 | 2022-03-25 | 2021-09-08 | 2022-03-30 | Capital | Approved | Planned/ Ongoing/ Executed | Green | System Stability | TPP | Common | Sustaining CAPEX Carryover | 0 | Complete | Complete | 2 | 0.4 | 0.4 | null
67 | High | P074 | Project Detail 67 | 2021-12-21 | 2023-07-25 | 2022-01-05 | 2023-07-25 | Revenue | Approved | Planned/ Ongoing/ Executed | Green | System Stability | CPP | Common | Revenue One-time | 0 | L3 | On-track | 8 | 8 | 8 | Delayed from baseline & running delayed
68 | High | P075 | Project Detail 68 | 2021-12-31 | 2022-11-27 | 2021-12-31 | 2022-11-27 | Capital | Approved | Planned/ Ongoing/ Executed | Green | System Stability | CPP | Common | Sustaining CAPEX New | 0.59701 | L1 | On-track | 30 | 1.5 | 1.5 | Delayed from baseline & running delayed
69 | High | P076 | Project Detail 69 | 2021-12-01 | 2023-12-26 | 2021-12-01 | 2023-12-26 | Capital | Approved | Planned/ Ongoing/ Executed | Green | System Stability | CPP | Common | Sustaining CAPEX New | 0 | L2 | On-track | 60 | 0 | 0 | Delayed from baseline & currently on-track
70 | High | P077 | Project Detail 70 | 2022-01-03 | 2023-03-31 | 2022-01-03 | 2023-03-31 | Capital | Approved | Planned/ Ongoing/ Executed | Green | System Stability | Fly Ash | Ash Management | Sustaining CAPEX New | 0 | L1 | On-track | 30 | 30 | 5 | Delayed from baseline & running delayed
71 | High | P078 | Project Detail 71 | 2021-04-16 | 2023-08-10 | 2021-04-16 | 2023-08-10 | Capital | Approved | Planned/ Ongoing/ Executed | Green | System Stability | Fly Ash | Ash Management | Sustaining CAPEX New | 0 | L1 | On-track | 130 | 130 | 30 | Delayed from baseline & running delayed
72 | High | P079 | Project Detail 72 | 2022-01-01 | 2024-04-16 | 2022-01-01 | 2024-04-16 | Capital | Approved | Planned/ Ongoing/ Executed | Green | System Stability | Fly Ash | Ash Management | Sustaining CAPEX New | 0 | L1 | On-track | 250 | 12.5 | 12.5 | null
73 | High | P081 | Project Detail 73 | 2021-03-01 | 2022-09-30 | 2021-03-01 | 2022-09-30 | Capital | Approved | Planned/ Ongoing/ Executed | Green | System Stability | Fly Ash | Ash Management | Sustaining CAPEX Carryover | 0 | L4 | On-track | 5.5 | 2 | 2 | null
74 | Medium | P082 | Project Detail 74 | null | null | null | null | Capital | Not Applicable | Dropped | null | System Stability | Fly Ash | Ash Management | Sustaining CAPEX New | 0 | Unavailable | Not yet started | 0 | 0 | 0 | null
75 | High | P083 | Project Detail 75 | 2020-12-31 | 2022-12-23 | 2020-12-31 | 2022-12-23 | Capital | Approved | Planned/ Ongoing/ Executed | Green | System Stability | BOP | Digitalization | Sustaining CAPEX New | 3.556 | L3 | On-track | 13 | 6 | 3.3 | Delayed from baseline & running delayed
76 | Medium | P084 | Project Detail 76 | 2022-04-30 | 2023-08-31 | null | null | Capital | Unapproved | On Hold | null | System Stability | CPP | ESG | Sustaining CAPEX New | 0 | Unavailable | Not yet started | 30 | 0 | 0 | null
77 | High | P085 | Project Detail 77 | 2021-09-01 | 2023-07-15 | 2021-09-01 | 2023-07-15 | Capital | Approved | Planned/ Ongoing/ Executed | Green | System Stability | BOP | ESG | Sustaining CAPEX New | 3.3465 | L1 | On-track | 26 | 0 | 0 | Delayed from baseline & running delayed
78 | Medium | P091 | Project Detail 78 | 2022-02-04 | 2022-05-20 | 2022-02-04 | 2022-07-05 | Revenue | Unapproved | Planned/ Ongoing/ Executed | Red | System Stability | CPP | Operations | Revenue One-time | 0 | L4 | Delayed | 0.12 | 0.12 | 0 | Delayed from baseline & running delayed
79 | Medium | P108 | Project Detail 79 | 2021-09-07 | 2022-05-14 | 2021-09-07 | 2022-08-05 | Revenue | Approved | Planned/ Ongoing/ Executed | Red | BTG Improvement | TPP | Boiler | Revenue One-time | 0 | L4 | Delayed | 8 | 8 | 8 | Delayed from baseline & currently on-track
81 | High | P111 | Project Detail 80 | 2021-12-01 | 2023-12-26 | 2021-12-01 | 2023-12-26 | Capital | Approved | Planned/ Ongoing/ Executed | Green | System Stability | TPP | Common | Sustaining CAPEX New | 0 | L2 | On-track | 315 | 7.5 | 7.5 | Delayed from baseline & currently on-track
82 | Medium | P112 | Project Detail 81 | 2021-02-01 | 2022-05-14 | 2021-02-01 | 2022-08-07 | Revenue | Approved | Planned/ Ongoing/ Executed | Red | BTG Improvement | TPP | Boiler | Revenue Regular | 0.053704 | L4 | Delayed | 0.2 | 0 | 0 | Delayed from baseline & currently on-track
83 | Medium | P113 | Project Detail 82 | 2021-02-01 | 2022-05-14 | 2021-02-01 | 2022-08-16 | Revenue | Approved | Planned/ Ongoing/ Executed | Red | BTG Improvement | TPP | Boiler | Revenue One-time | 0.011815 | L4 | Delayed | 0.3 | 0 | 0 | Delayed from baseline & currently on-track
80 | Medium | P109 | Project Detail 83 | 2021-07-01 | 2022-05-14 | 2021-07-01 | 2022-07-30 | Revenue | Approved | Planned/ Ongoing/ Executed | Red | BTG Improvement | TPP | Boiler | Revenue One-time | 0.19326 | L4 | Delayed | 1.75 | 1.75 | 1.75 | Delayed from baseline & currently on-track
84 | Medium | P114 | Project Detail 84 | 2022-01-05 | 2022-02-25 | 2022-01-06 | 2022-08-15 | Not required | Not Applicable | Planned/ Ongoing/ Executed | Red | BTG Improvement | TPP | Boiler | Not required | 0.024158 | L4 | Delayed | 0 | 0 | 0 | Delayed from baseline & currently on-track
85 | Medium | P115 | Project Detail 85 | 2021-10-01 | 2022-02-27 | 2021-10-01 | 2022-07-10 | Not required | Not Applicable | Planned/ Ongoing/ Executed | Red | BTG Improvement | TPP | Turbine | Not required | 0.080556 | L4 | Delayed | 0 | 0 | 0 | Delayed from baseline & currently on-track
86 | High | P116 | Project Detail 86 | 2022-02-01 | 2023-05-01 | 2022-02-01 | 2023-05-01 | Revenue | Approved | Planned/ Ongoing/ Executed | Green | System Stability | TPP | Common | Revenue One-time | 0 | L3 | On-track | 0.3 | 0.3 | 0.3 | Delayed from baseline & currently on-track
87 | Medium | P117 | Project Detail 87 | null | null | null | null | Capital | Unapproved | On Hold | null | System Stability | TPP | Common | Project CAPEX | 0 | Unavailable | Not yet started | 1450 | 0 | 0 | null
88 | Medium | P118 | Project Detail 88 | 2022-06-01 | 2022-07-31 | 2022-06-01 | 2022-07-31 | null | null | Planned/ Ongoing/ Executed | Green | BTG Improvement | CPP | Boiler | null | 0 | L1 | On-track | null | null | null | null
89 | Medium | P119 | Project Detail 89 | 2022-06-01 | 2022-07-31 | 2022-06-01 | 2022-07-31 | null | null | Planned/ Ongoing/ Executed | Green | System Stability | Water | Water Security | null | 0 | L1 | On-track | null | null | null | null
90 | High | P120 | Project Detail 90 | 2022-04-13 | 2022-07-31 | 2022-04-13 | 2022-07-31 | null | null | Planned/ Ongoing/ Executed | Green | System Stability | Coal | Coal | null | 0 | L1 | On-track | null | null | null | null
91 | High | P121 | Project Detail 91 | 2022-04-01 | 2022-08-10 | 2022-06-01 | 2022-08-10 | null | null | Planned/ Ongoing/ Executed | Green | System Stability | Coal | Coal | null | 0 | L4 | On-track | null | null | null | null
92 | Medium | P122 | Project Detail 92 | 2022-06-01 | null | null | null | null | null | On Hold | null | System Stability | Coal | Coal | null | 0 | Unavailable | Not yet started | null | null | null | null
93 | Low | P123 | Project Detail 93 | null | 2022-05-31 | null | 2022-07-31 | Capital | null | null | null | null | TPP | null | Sustaining CAPEX Carryover | null | L4 | Delayed | null | null | null | null
94 | Low | P124 | Project Detail 94 | null | 2022-09-30 | null | 2022-09-30 | Capital | null | null | null | null | Fly Ash | null | Sustaining CAPEX Carryover | null | L4 | On-track | null | null | null | null
96 | Low | P126 | Project Detail 95 | null | 2023-03-31 | null | 2023-10-31 | Capital | null | null | null | null | TPP | null | Sustaining CAPEX Carryover | null | L4 | Delayed | null | null | null | null
97 | Low | P127 | Project Detail 96 | null | 2022-12-31 | null | 2023-03-31 | Capital | null | null | null | null | TPP | null | Sustaining CAPEX Carryover | null | L4 | Delayed | null | null | null | null
98 | Low | P128 | Project Detail 97 | null | 2022-08-31 | null | 2022-08-31 | Capital | null | null | null | null | TPP | null | Sustaining CAPEX Carryover | null | L4 | On-track | null | null | null | null
99 | Low | P129 | Project Detail 98 | null | 2024-03-31 | null | 2024-03-31 | Capital | null | null | null | null | CPP | null | Sustaining CAPEX Carryover | null | L4 | On-track | null | null | null | null
100 | Low | P130 | Project Detail 99 | null | 2023-03-31 | null | 2023-03-31 | Capital | null | null | null | null | CPP | null | Sustaining CAPEX Carryover | null | L4 | On-track | null | null | null | null
101 | Low | P131 | Project Detail 100 | null | 2022-06-30 | null | 2022-07-31 | Capital | null | null | null | null | CPP | null | Sustaining CAPEX Carryover | null | L4 | Delayed | null | null | null | null
102 | Low | P132 | Project Detail 101 | null | 2022-04-30 | null | 2022-06-30 | Capital | null | null | null | null | TPP | null | Sustaining CAPEX Carryover | null | L4 | Delayed | null | null | null | null
103 | Low | P133 | Project Detail 102 | null | 2023-06-30 | null | 2023-06-30 | Capital | null | null | null | null | TPP | null | Sustaining CAPEX New | null | L4 | On-track | null | null | null | null
104 | Low | P134 | Project Detail 103 | null | 2022-06-30 | null | 2022-07-31 | Capital | null | null | null | null | Fly Ash | null | Sustaining CAPEX New | null | L4 | Delayed | null | null | null | null
105 | Low | P135 | Project Detail 104 | null | 2022-08-31 | null | 2022-08-31 | Capital | null | null | null | null | CPP | null | Sustaining CAPEX New | null | L4 | On-track | null | null | null | null
106 | Low | P136 | Project Detail 105 | null | 2022-12-31 | null | 2022-12-31 | Capital | null | null | null | null | TPP | null | Sustaining CAPEX New | null | L4 | On-track | null | null | null | null
107 | Low | P137 | Project Detail 106 | null | 2022-06-30 | 2022-05-31 | 2022-08-31 | Capital | null | null | null | null | CPP | null | null | null | L4 | Delayed | null | null | null | null
108 | Low | P138 | Project Detail 107 | null | 2022-09-30 | null | 2022-09-30 | Capital | null | null | null | null | TPP | null | Sustaining CAPEX New | null | L4 | On-track | null | null | null | null
109 | Low | P139 | Project Detail 108 | null | 2022-12-31 | null | 2023-02-28 | Capital | null | null | null | null | TPP | null | Sustaining CAPEX New | null | L4 | Delayed | null | null | null | null
110 | Low | P140 | Project Detail 109 | null | 2023-03-31 | null | 2023-03-31 | Capital | null | null | null | null | TPP | null | Sustaining CAPEX New | null | L4 | On-track | null | null | null | null
111 | Low | P141 | Project Detail 110 | null | 2022-06-30 | null | 2022-07-31 | Capital | null | null | null | null | CPP | null | Sustaining CAPEX Carryover | null | L4 | Delayed | null | null | null | null
112 | Low | P142 | Project Detail 111 | null | null | null | null | Capital | null | null | null | null | Fly Ash | null | Sustaining CAPEX New | null | Unavailable | Unavailable | null | null | null | null